# ACC Daily Report - Parsed Output

Project: Folsom Care Complex at Broadstone Phase II

Date: 2026-02-02

Source: Daily Trade Meeting Transcript

## 1. Work Log (Copy/Paste to ACC)

| Company | Discipline | # Workers | Hours | Work Performed |
| --- | --- | --- | --- | --- |
| The Boldt Company | Mix Crew / Self-Perform | 3 | 24 | General support, site coordination |
| Anning-Johnson Company | Decking/Framing | ? | ? | Fireproofing area setup, welding coordination - VERIFY HEADCOUNT |
| C&I Fireproofing | Fireproofing | 3 | 24 | Setup and tarps today, material delivery tomorrow, starting SE corner floors 5-10 working north |
| Mercury Mechanical | Mechanical | 5 | 40 | Mechanical work in progress |
| Mark III Construction | Plumbing | 5 | 40 | Guy sleeves layout and install, floor 3 |
| Mark III Construction | Electrical | 13 | 104 | Electrical work in progress |
| Archuleta | Framing/Flashing | 5 | 40 | East side flashing coordination, awaiting answers to proceed |
| Concrete North | Camblin Steel / Rebar | 4 | 32 | Rebar installation floor 2-3, ready for inspection Thursday |
| Conxtech | Steel Structure | ? | ? | Deck supports install, 5 of 1 lines completed - VERIFY HEADCOUNT |
| MTN Waterproofing | Waterproofing | ? | ? | Edge of slab waterproofing - delivering today - VERIFY HEADCOUNT |
| Pacific Stair Corporation | Stair Install | ? | ? | Stairs work if on site - VERIFY |

TOTALS: ~38+ workers (some headcounts need verification)

## 2. Weather

63°F and sunny. No rain in forecast.

## 3. Safety Observations

Shout-outs:

- Corporate visitors noted this is the cleanest job site they’ve ever seen - housekeeping top notch

Risks/Observations:

- Welding above requires bottom area to be cordoned off (AJ notified)

- Rebar found bent up on roof - caps added (good catch by crew)

- Fireproofing using CAUTION tape (not danger tape) - crews stay out of taped areas regardless

- Stair 3 closed: Someone went through 2x4 blockade to use stairs 1-2. First landing is 6+ ft = fall protection violation. Signs being posted.

- Lifts not yet available to 2nd floor (waiting on pork chops/cable) - using ladders

- Ladder safety reminder: Don’t stand higher than waist on top rung - get taller ladder or taller person

## 4. Inspections

Passed:

Floor flatness, Building steel substrate, First floor top track and clip

Scheduled:

Linac walls concrete placement, Level 3 rebar (2/24-25), Concrete placement full bases (today), NW side concrete placement, Deck supports 3 lines (tomorrow AM)

## 5. Deliveries

- Today: MTN Waterproofing materials (edge of slab)

- Today: Level 1 panels - first month arriving (Boldt self-offloading)

- Tomorrow: Load of materials + trusses (traffic on front road, entry from south)

- Tomorrow: Fireproofing material arriving, work starts in morning

## 6. Key Coordination Items

- Pan decking above elevator shafts: Confirmed can be pulled up without replacement. Angles to be installed after deck is poured.

- East side flashing (Archuleta): Waiting on answers before proceeding - super to follow up today

- Survey/Layout issue Floor 2: Control points showing 11/30" off. Dusty being consulted. May need solution before wall layout.

- Brake test (floor 2): Calvin to notify when scheduled - will open up more work area

- Friday: Dropping hangers from roof (10 to 5 area) - timing after fireproofing

- Trucks tomorrow: Moving trucks from current side, deliveries can stage at new location

## Items Needing Verification

- AJ (Anning-Johnson) headcount - unclear from transcript

- Conxtech headcount - unclear from transcript

- MTN Waterproofing headcount - not stated

- Pacific Stair - confirm if on site today

Parsed from meeting transcript by AI. Review before submission.